## summary
summary |  |  |  |  | Current Date | 2026-08-15
|  | 955 | 50000 | 43276.5 | 421 | 26067 | 23460.3 | 515 | 21525 | 19372.5 | 936 | 50000 | 42832.8 | -19 | 0 | -443.7
Task Code | Task Name | Benchmark Hours | Benchmark Bill | Benchmark FBLR | Actuals To Date Hours | Actuals To Date Bill | Actuals To Date FBLR | Estimate to Complete Hours | Estimate to Complete Bill | Estimate to Complete FBLR | Estimate at Completion Hours | Estimate at Completion Bill | Estimate at Completion FBLR | Variance Hours | Variance Bill | Variance FBLR
T-101 | Requirements gathering | 30 | 3000 | 2700 | 28 | 2800 | 2520 | 0 | 0 | 0 | 28 | 2800 | 2520 | -2 | -200 | -180
T-102 | Scope definition | 30 | 2600 | 2340 | 34 | 2980 | 2682 | 0 | 0 | 0 | 34 | 2980 | 2682 | 4 | 380 | 342
T-103 | Project planning | 60 | 5200 | 4680 | 55 | 4800 | 4320 | 0 | 0 | 0 | 55 | 4800 | 4320 | -5 | -400 | -360
T-104 | Solution design | 60 | 4100 | 3690 | 55 | 3785 | 3406.5 | 0 | 0 | 0 | 55 | 3785 | 3406.5 | -5 | -315 | -283.5
T-105 | Database design | 60 | 4100 | 3690 | 60 | 4163 | 3746.7 | 0 | 0 | 0 | 60 | 4163 | 3746.7 | 0 | 63 | 56.7
T-106 | Front-end development | 150 | 4410 | 3969 | 94 | 3066 | 2759.4 | 50 | 1470 | 1323 | 144 | 4536 | 4082.4 | -6 | 126 | 113.4
T-107 | Back-end development | 150 | 6930 | 6237 | 95 | 4473 | 4025.7 | 50 | 2310 | 2079 | 145 | 6783 | 6104.7 | -5 | -147 | -132.3
T-108 | Unit testing | 100 | 2940 | 2646 | 0 | 0 | 0 | 100 | 2940 | 2646 | 100 | 2940 | 2646 | 0 | 0 | 0
T-109 | Integration testing | 100 | 2940 | 2646 | 0 | 0 | 0 | 100 | 2940 | 2646 | 100 | 2940 | 2646 | 0 | 0 | 0
T-110 | User acceptance testing | 100 | 3360 | 3024 | 0 | 0 | 0 | 100 | 3360 | 3024 | 100 | 3360 | 3024 | 0 | 0 | 0
T-111 | Production deployment | 100 | 7140 | 6426 | 0 | 0 | 0 | 100 | 7140 | 6426 | 100 | 7140 | 6426 | 0 | 0 | 0
T-112 | Project closure | 15 | 1365 | 1228.5 | 0 | 0 | 0 | 15 | 1365 | 1228.5 | 15 | 1365 | 1228.5 | 0 | 0 | 0
T-Con | Contingency |  | 1915 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2408 |  | 0 | 493

## actuals
actuals
Task Code | Task Name | Employee Title | Employee Number | Employee Name | Week Ending | Hours | Bill Rate/Hour | FLBR Rate/Hour | Forecast Bill | Forecast FBLR
T-101 | Requirements gathering | Director | 1 | Ethan Carter | 2026-07-04 | 7 | 100 | 90 | 700 | 630
T-101 | Requirements gathering | Director | 1 | Ethan Carter | 2026-07-11 | 5 | 100 | 90 | 500 | 450
T-102 | Scope definition | Director | 1 | Ethan Carter | 2026-07-11 | 5 | 100 | 90 | 500 | 450
T-102 | Scope definition | Director | 1 | Ethan Carter | 2026-07-18 | 8 | 100 | 90 | 800 | 720
T-101 | Requirements gathering | Director | 2 | Olivia Bennett | 2026-07-04 | 8 | 100 | 90 | 800 | 720
T-101 | Requirements gathering | Director | 2 | Olivia Bennett | 2026-07-11 | 8 | 100 | 90 | 800 | 720
T-103 | Project planning | Director | 2 | Olivia Bennett | 2026-07-11 | 11 | 100 | 90 | 1100 | 990
T-103 | Project planning | Director | 2 | Olivia Bennett | 2026-07-18 | 9 | 100 | 90 | 900 | 810
T-103 | Project planning | Manager | 3 | Liam Foster | 2026-07-11 | 18 | 80 | 72 | 1440 | 1296
T-103 | Project planning | Manager | 3 | Liam Foster | 2026-07-18 | 17 | 80 | 72 | 1360 | 1224
T-105 | Database design | Manager | 3 | Liam Foster | 2026-07-25 | 13 | 80 | 72 | 1040 | 936
T-105 | Database design | Manager | 3 | Liam Foster | 2026-08-01 | 11 | 84 | 75.6 | 924 | 831.6
T-102 | Scope definition | Manager | 4 | Sophia Mitchell | 2026-07-11 | 7 | 80 | 72 | 560 | 504
T-102 | Scope definition | Manager | 4 | Sophia Mitchell | 2026-07-18 | 14 | 80 | 72 | 1120 | 1008
T-104 | Solution design | Manager | 4 | Sophia Mitchell | 2026-07-25 | 4 | 80 | 72 | 320 | 288
T-104 | Solution design | Manager | 4 | Sophia Mitchell | 2026-08-01 | 15 | 84 | 75.6 | 1260 | 1134
T-104 | Solution design | Senior Engineer | 5 | Noah Turner | 2026-07-25 | 21 | 60 | 54 | 1260 | 1134
T-104 | Solution design | Senior Engineer | 5 | Noah Turner | 2026-08-01 | 15 | 63 | 56.7 | 945 | 850.5
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | 2026-08-08 | 12 | 63 | 56.7 | 756 | 680.4
T-105 | Database design | Senior Engineer | 6 | Amelia Brooks | 2026-07-25 | 23 | 60 | 54 | 1380 | 1242
T-105 | Database design | Senior Engineer | 6 | Amelia Brooks | 2026-08-01 | 13 | 63 | 56.7 | 819 | 737.1
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | 2026-08-15 | 14 | 63 | 56.7 | 882 | 793.8
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | 2026-08-08 | 35 | 21 | 18.9 | 735 | 661.5
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | 2026-08-15 | 33 | 21 | 18.9 | 693 | 623.7
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | 2026-08-08 | 12 | 63 | 56.7 | 756 | 680.4
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | 2026-08-15 | 11 | 63 | 56.7 | 693 | 623.7
T-107 | Back-end development | Engineer | 7 | Mason Reed | 2026-08-08 | 39 | 42 | 37.8 | 1638 | 1474.2
T-107 | Back-end development | Engineer | 7 | Mason Reed | 2026-08-15 | 33 | 42 | 37.8 | 1386 | 1247.4

## input forecasts
input forecasts
[10 empty] | 48825 | 43942.5 | 955 | 2026-07-04 | 2026-07-11 | 2026-07-18 | 2026-07-25 | 2026-08-01 | 2026-08-08 | 2026-08-15 | 2026-08-22 | 2026-08-29 | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26
Task Code | Task Name | Employee Title | Employee Number | Employee Name | Bill Rate/Hour | FBLR/Hour | Actuals To Date Hours | Actuals To Date Bill | Actuals To Date FBLR | Forecast Bill | Forecast FBLR | Forecast Hours | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
T-101 | Requirements gathering | Director | 1 | Ethan Carter | 105 | 94.5 | 12 | 1200 | 1080 | 1050 | 945 | 10 | W1: 5; W2: 5
T-101 | Requirements gathering | Director | 2 | Olivia Bennett | 105 | 94.5 | 16 | 1600 | 1440 | 2100 | 1890 | 20 | W1: 10; W2: 10
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-102 | Scope definition | Director | 1 | Ethan Carter | 105 | 94.5 | 13 | 1300 | 1170 | 1050 | 945 | 10 | W2: 5; W3: 5
T-102 | Scope definition | Manager | 4 | Sophia Mitchell | 84 | 75.6 | 21 | 1680 | 1512 | 1680 | 1512 | 20 | W2: 10; W3: 10
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-103 | Project planning | Director | 2 | Olivia Bennett | 105 | 94.5 | 20 | 2000 | 1800 | 2100 | 1890 | 20 | W2: 10; W3: 10
T-103 | Project planning | Manager | 3 | Liam Foster | 84 | 75.6 | 35 | 2800 | 2520 | 3360 | 3024 | 40 | W2: 20; W3: 20
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-104 | Solution design | Manager | 4 | Sophia Mitchell | 84 | 75.6 | 19 | 1580 | 1422 | 1680 | 1512 | 20 | W4: 10; W5: 10
T-104 | Solution design | Senior Engineer | 5 | Noah Turner | 63 | 56.7 | 36 | 2205 | 1984.5 | 2520 | 2268 | 40 | W4: 20; W5: 20
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-105 | Database design | Manager | 3 | Liam Foster | 84 | 75.6 | 24 | 1964 | 1767.6 | 1680 | 1512 | 20 | W4: 10; W5: 10
T-105 | Database design | Senior Engineer | 6 | Amelia Brooks | 63 | 56.7 | 36 | 2199 | 1979.1 | 2520 | 2268 | 40 | W4: 20; W5: 20
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | 63 | 56.7 | 26 | 1638 | 1474.2 | 1890 | 1701 | 30 | W6: 10; W7: 10; W8: 10
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | 21 | 18.9 | 68 | 1428 | 1285.2 | 2520 | 2268 | 120 | W6: 40; W7: 40; W8: 40
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | 63 | 56.7 | 23 | 1449 | 1304.1 | 1890 | 1701 | 30 | W6: 10; W7: 10; W8: 10
T-107 | Back-end development | Engineer | 7 | Mason Reed | 42 | 37.8 | 72 | 3024 | 2721.6 | 5040 | 4536 | 120 | W6: 40; W7: 40; W8: 40
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-108 | Unit testing | Senior Engineer | 6 | Amelia Brooks | 63 | 56.7 | 0 | 0 | 0 | 1260 | 1134 | 20 | W9: 10; W10: 10
T-108 | Unit testing | Apprentice | 9 | Lucas Parker | 21 | 18.9 | 0 | 0 | 0 | 1680 | 1512 | 80 | W9: 40; W10: 40
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-109 | Integration testing | Senior Engineer | 5 | Noah Turner | 63 | 56.7 | 0 | 0 | 0 | 1260 | 1134 | 20 | W9: 10; W10: 10
T-109 | Integration testing | Apprentice | 10 | Grace Sullivan | 21 | 18.9 | 0 | 0 | 0 | 1680 | 1512 | 80 | W9: 40; W10: 40
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-110 | User acceptance testing | Manager | 3 | Liam Foster | 84 | 75.6 | 0 | 0 | 0 | 1680 | 1512 | 20 | W9: 10; W10: 10
T-110 | User acceptance testing | Apprentice | 9 | Lucas Parker | 21 | 18.9 | 0 | 0 | 0 | 1680 | 1512 | 80 | W9: 40; W10: 40
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-111 | Production deployment | Manager | 4 | Sophia Mitchell | 84 | 75.6 | 0 | 0 | 0 | 3360 | 3024 | 40 | W11: 20; W12: 20
T-111 | Production deployment | Senior Engineer | 5 | Noah Turner | 63 | 56.7 | 0 | 0 | 0 | 3780 | 3402 | 60 | W11: 30; W12: 30
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-112 | Project closure | Director | 2 | Olivia Bennett | 105 | 94.5 | 0 | 0 | 0 | 525 | 472.5 | 5 | W13: 5
T-112 | Project closure | Manager | 4 | Sophia Mitchell | 84 | 75.6 | 0 | 0 | 0 | 840 | 756 | 10 | W13: 10
| 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## fact forecasts
fact forecasts
Task Code | Task Name | Employee Title | Employee Number | Employee Name | Week Number | Week Ending | Financial Year | Hours | Bill Rate/Hour | FLBR Rate/Hour | Forecast Bill | Forecast FBLR
T-101 | Requirements gathering | Director | 1 | Ethan Carter | W1 | 2026-07-04 | FY26 | 5 | 100 | 90 | 500 | 450
T-101 | Requirements gathering | Director | 1 | Ethan Carter | W2 | 2026-07-11 | FY26 | 5 | 100 | 90 | 500 | 450
T-102 | Scope definition | Director | 1 | Ethan Carter | W2 | 2026-07-11 | FY26 | 5 | 100 | 90 | 500 | 450
T-102 | Scope definition | Director | 1 | Ethan Carter | W3 | 2026-07-18 | FY26 | 5 | 100 | 90 | 500 | 450
T-101 | Requirements gathering | Director | 2 | Olivia Bennett | W1 | 2026-07-04 | FY26 | 10 | 100 | 90 | 1000 | 900
T-101 | Requirements gathering | Director | 2 | Olivia Bennett | W2 | 2026-07-11 | FY26 | 10 | 100 | 90 | 1000 | 900
T-103 | Project planning | Director | 2 | Olivia Bennett | W2 | 2026-07-11 | FY26 | 10 | 100 | 90 | 1000 | 900
T-103 | Project planning | Director | 2 | Olivia Bennett | W3 | 2026-07-18 | FY26 | 10 | 100 | 90 | 1000 | 900
T-103 | Project planning | Manager | 3 | Liam Foster | W2 | 2026-07-11 | FY26 | 20 | 80 | 72 | 1600 | 1440
T-103 | Project planning | Manager | 3 | Liam Foster | W3 | 2026-07-18 | FY26 | 20 | 80 | 72 | 1600 | 1440
T-105 | Database design | Manager | 3 | Liam Foster | W4 | 2026-07-25 | FY26 | 10 | 80 | 72 | 800 | 720
T-105 | Database design | Manager | 3 | Liam Foster | W5 | 2026-08-01 | FY27 | 10 | 84 | 75.6 | 840 | 756
T-102 | Scope definition | Manager | 4 | Sophia Mitchell | W2 | 2026-07-11 | FY26 | 10 | 80 | 72 | 800 | 720
T-102 | Scope definition | Manager | 4 | Sophia Mitchell | W3 | 2026-07-18 | FY26 | 10 | 80 | 72 | 800 | 720
T-104 | Solution design | Manager | 4 | Sophia Mitchell | W4 | 2026-07-25 | FY26 | 10 | 80 | 72 | 800 | 720
T-104 | Solution design | Manager | 4 | Sophia Mitchell | W5 | 2026-08-01 | FY27 | 10 | 84 | 75.6 | 840 | 756
T-104 | Solution design | Senior Engineer | 5 | Noah Turner | W4 | 2026-07-25 | FY26 | 20 | 60 | 54 | 1200 | 1080
T-104 | Solution design | Senior Engineer | 5 | Noah Turner | W5 | 2026-08-01 | FY27 | 20 | 63 | 56.7 | 1260 | 1134
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | W6 | 2026-08-08 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-105 | Database design | Senior Engineer | 6 | Amelia Brooks | W4 | 2026-07-25 | FY26 | 20 | 60 | 54 | 1200 | 1080
T-105 | Database design | Senior Engineer | 6 | Amelia Brooks | W5 | 2026-08-01 | FY27 | 20 | 63 | 56.7 | 1260 | 1134
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | W7 | 2026-08-15 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-106 | Front-end development | Senior Engineer | 5 | Noah Turner | W8 | 2026-08-22 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | W6 | 2026-08-08 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | W7 | 2026-08-15 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-106 | Front-end development | Apprentice | 9 | Lucas Parker | W8 | 2026-08-22 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | W6 | 2026-08-08 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | W7 | 2026-08-15 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-107 | Back-end development | Senior Engineer | 6 | Amelia Brooks | W8 | 2026-08-22 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-107 | Back-end development | Engineer | 7 | Mason Reed | W6 | 2026-08-08 | FY27 | 40 | 42 | 37.8 | 1680 | 1512
T-107 | Back-end development | Engineer | 7 | Mason Reed | W7 | 2026-08-15 | FY27 | 40 | 42 | 37.8 | 1680 | 1512
T-107 | Back-end development | Engineer | 7 | Mason Reed | W8 | 2026-08-22 | FY27 | 40 | 42 | 37.8 | 1680 | 1512
T-108 | Unit testing | Senior Engineer | 6 | Amelia Brooks | W9 | 2026-08-29 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-108 | Unit testing | Senior Engineer | 6 | Amelia Brooks | W10 | 2026-09-05 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-108 | Unit testing | Apprentice | 9 | Lucas Parker | W9 | 2026-08-29 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-108 | Unit testing | Apprentice | 9 | Lucas Parker | W10 | 2026-09-05 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-109 | Integration testing | Senior Engineer | 5 | Noah Turner | W9 | 2026-08-29 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-109 | Integration testing | Senior Engineer | 5 | Noah Turner | W10 | 2026-09-05 | FY27 | 10 | 63 | 56.7 | 630 | 567
T-109 | Integration testing | Apprentice | 10 | Grace Sullivan | W9 | 2026-08-29 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-109 | Integration testing | Apprentice | 10 | Grace Sullivan | W10 | 2026-09-05 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-110 | User acceptance testing | Manager | 3 | Liam Foster | W9 | 2026-08-29 | FY27 | 10 | 84 | 75.6 | 840 | 756
T-110 | User acceptance testing | Manager | 3 | Liam Foster | W10 | 2026-09-05 | FY27 | 10 | 84 | 75.6 | 840 | 756
T-110 | User acceptance testing | Apprentice | 9 | Lucas Parker | W9 | 2026-08-29 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-110 | User acceptance testing | Apprentice | 9 | Lucas Parker | W10 | 2026-09-05 | FY27 | 40 | 21 | 18.9 | 840 | 756
T-111 | Production deployment | Manager | 4 | Sophia Mitchell | W11 | 2026-09-12 | FY27 | 20 | 84 | 75.6 | 1680 | 1512
T-111 | Production deployment | Manager | 4 | Sophia Mitchell | W12 | 2026-09-19 | FY27 | 20 | 84 | 75.6 | 1680 | 1512
T-111 | Production deployment | Senior Engineer | 5 | Noah Turner | W11 | 2026-09-12 | FY27 | 30 | 63 | 56.7 | 1890 | 1701
T-111 | Production deployment | Senior Engineer | 5 | Noah Turner | W12 | 2026-09-19 | FY27 | 30 | 63 | 56.7 | 1890 | 1701
T-112 | Project closure | Director | 2 | Olivia Bennett | W13 | 2026-09-26 | FY27 | 5 | 105 | 94.5 | 525 | 472.5
T-112 | Project closure | Manager | 4 | Sophia Mitchell | W13 | 2026-09-26 | FY27 | 10 | 84 | 75.6 | 840 | 756

## input rates
input rates
Rate Type | Employee Number | FY26 | FY27 | Rate Type | Employee Number | FY26 | FY27 | Rate Type | Employee Number | FY26 | FY27
Bill Rate/Hour | 1 | 100 | 105 | FBLR/Hour | 1 | 90 | 94.5 | Raw Rate/Hour | 1 | 45 | 47.25
Bill Rate/Hour | 2 | 100 | 105 | FBLR/Hour | 2 | 90 | 94.5 | Raw Rate/Hour | 2 | 45 | 47.25
Bill Rate/Hour | 3 | 80 | 84 | FBLR/Hour | 3 | 72 | 75.6 | Raw Rate/Hour | 3 | 36 | 37.8
Bill Rate/Hour | 4 | 80 | 84 | FBLR/Hour | 4 | 72 | 75.6 | Raw Rate/Hour | 4 | 36 | 37.8
Bill Rate/Hour | 5 | 60 | 63 | FBLR/Hour | 5 | 54 | 56.7 | Raw Rate/Hour | 5 | 27 | 28.35
Bill Rate/Hour | 6 | 60 | 63 | FBLR/Hour | 6 | 54 | 56.7 | Raw Rate/Hour | 6 | 27 | 28.35
Bill Rate/Hour | 7 | 40 | 42 | FBLR/Hour | 7 | 36 | 37.8 | Raw Rate/Hour | 7 | 18 | 18.9
Bill Rate/Hour | 8 | 40 | 42 | FBLR/Hour | 8 | 36 | 37.8 | Raw Rate/Hour | 8 | 18 | 18.9
Bill Rate/Hour | 9 | 20 | 21 | FBLR/Hour | 9 | 18 | 18.9 | Raw Rate/Hour | 9 | 9 | 9.45
Bill Rate/Hour | 10 | 20 | 21 | FBLR/Hour | 10 | 18 | 18.9 | Raw Rate/Hour | 10 | 9 | 9.45

## dim rates
dim rates
Rate Type | Employee Number | FY | Rate
Bill Rate/Hour | 1 | FY26 | 100
Bill Rate/Hour | 1 | FY27 | 105
Bill Rate/Hour | 2 | FY26 | 100
Bill Rate/Hour | 2 | FY27 | 105
Bill Rate/Hour | 3 | FY26 | 80
Bill Rate/Hour | 3 | FY27 | 84
Bill Rate/Hour | 4 | FY26 | 80
Bill Rate/Hour | 4 | FY27 | 84
Bill Rate/Hour | 5 | FY26 | 60
Bill Rate/Hour | 5 | FY27 | 63
Bill Rate/Hour | 6 | FY26 | 60
Bill Rate/Hour | 6 | FY27 | 63
Bill Rate/Hour | 7 | FY26 | 40
Bill Rate/Hour | 7 | FY27 | 42
Bill Rate/Hour | 8 | FY26 | 40
Bill Rate/Hour | 8 | FY27 | 42
Bill Rate/Hour | 9 | FY26 | 20
Bill Rate/Hour | 9 | FY27 | 21
Bill Rate/Hour | 10 | FY26 | 20
Bill Rate/Hour | 10 | FY27 | 21
FBLR/Hour | 1 | FY26 | 90
FBLR/Hour | 1 | FY27 | 94.5
FBLR/Hour | 2 | FY26 | 90
FBLR/Hour | 2 | FY27 | 94.5
FBLR/Hour | 3 | FY26 | 72
FBLR/Hour | 3 | FY27 | 75.6
FBLR/Hour | 4 | FY26 | 72
FBLR/Hour | 4 | FY27 | 75.6
FBLR/Hour | 5 | FY26 | 54
FBLR/Hour | 5 | FY27 | 56.7
FBLR/Hour | 6 | FY26 | 54
FBLR/Hour | 6 | FY27 | 56.7
FBLR/Hour | 7 | FY26 | 36
FBLR/Hour | 7 | FY27 | 37.8
FBLR/Hour | 8 | FY26 | 36
FBLR/Hour | 8 | FY27 | 37.8
FBLR/Hour | 9 | FY26 | 18
FBLR/Hour | 9 | FY27 | 18.9
FBLR/Hour | 10 | FY26 | 18
FBLR/Hour | 10 | FY27 | 18.9
Raw Rate/Hour | 1 | FY26 | 45
Raw Rate/Hour | 1 | FY27 | 47.25
Raw Rate/Hour | 2 | FY26 | 45
Raw Rate/Hour | 2 | FY27 | 47.25
Raw Rate/Hour | 3 | FY26 | 36
Raw Rate/Hour | 3 | FY27 | 37.8
Raw Rate/Hour | 4 | FY26 | 36
Raw Rate/Hour | 4 | FY27 | 37.8
Raw Rate/Hour | 5 | FY26 | 27
Raw Rate/Hour | 5 | FY27 | 28.35
Raw Rate/Hour | 6 | FY26 | 27
Raw Rate/Hour | 6 | FY27 | 28.35
Raw Rate/Hour | 7 | FY26 | 18
Raw Rate/Hour | 7 | FY27 | 18.9
Raw Rate/Hour | 8 | FY26 | 18
Raw Rate/Hour | 8 | FY27 | 18.9
Raw Rate/Hour | 9 | FY26 | 9
Raw Rate/Hour | 9 | FY27 | 9.45
Raw Rate/Hour | 10 | FY26 | 9
Raw Rate/Hour | 10 | FY27 | 9.45

## dim dates
dim dates
Week Number | Week Ending | Financial Year
W1 | 2026-07-04 | FY26
W2 | 2026-07-11 | FY26
W3 | 2026-07-18 | FY26
W4 | 2026-07-25 | FY26
W5 | 2026-08-01 | FY27
W6 | 2026-08-08 | FY27
W7 | 2026-08-15 | FY27
W8 | 2026-08-22 | FY27
W9 | 2026-08-29 | FY27
W10 | 2026-09-05 | FY27
W11 | 2026-09-12 | FY27
W12 | 2026-09-19 | FY27
W13 | 2026-09-26 | FY27
Formulas:
Week Ending = [Week Ending, row above]+7

## dim employees
dim employees | - | -
Employee Title | Employee Number | Employee Name
Director | 1 | Ethan Carter
Director | 2 | Olivia Bennett
Manager | 3 | Liam Foster
Manager | 4 | Sophia Mitchell
Senior Engineer | 5 | Noah Turner
Senior Engineer | 6 | Amelia Brooks
Engineer | 7 | Mason Reed
Engineer | 8 | Charlotte Hayes
Apprentice | 9 | Lucas Parker
Apprentice | 10 | Grace Sullivan

## dim tasks
dim tasks
Task Code | Task Name
T-101 | Requirements gathering
T-102 | Scope definition
T-103 | Project planning
T-104 | Solution design
T-105 | Database design
T-106 | Front-end development
T-107 | Back-end development
T-108 | Unit testing
T-109 | Integration testing
T-110 | User acceptance testing
T-111 | Production deployment
T-112 | Project closure